## Overview
📋 Digital Verification Test Plan
Project: Vortex RISC-V SIMT GPGPU UVM Verification ¦ DUT: Vortex GPGPU (RV32IMAF, RTL @7a52ee5 + local fixes) ¦ Date: 2026-09-07 ¦ Engineer: Samuel Moussa
Workbook Index
Test Plan | Test items, cases, stimulus, pass criteria, intent | Sheet 1
Traceability Matrix | Spec section ↔ Requirement ↔ Test Case + closure % | Sheet 2
Feature Coverage | Feature, cascaded & negative scenario coverage | Sheet 3
Corner Cases | Data corner cases, toggle coverage | Sheet 4
Test Environment | Methodology, tools, DUT configuration | Sheet 5
Sign-off & Review | Approval signatures, review comments | Sheet 6
Revision History | Document version log | Sheet 7
Priority Legend
P0 | Critical — must pass before tapeout
P1 | High — must pass before sign-off
P2 | Medium — best effort
Status Legend
PASS | Test case passed all criteria
FAIL | Test case failed one or more criteria
WIP | Work in progress
BLOCK | Blocked by upstream issue
N/A | Not applicable for this DUT config

## Test Plan
Test Plan — Main Table
Test Item ID | Test Item Name | Feature Under Test | Test Case Definition | Stimulus / Approach | Expected Output | Pass Criteria | Intent of Testing | Cascaded Features (Mix & Match) | Negative Scenarios | Data: Corner Cases | Toggle Coverage | Priority | Status | Notes / References
TP-01 | Tag/ID width derivation (C1) | AXI/mem tag width | UVM tag width must equal RTL VX_MEM_TAG_WIDTH, not a hardcoded constant | Elaborate + read plusarg vs RTL param, assert equal | Elaboration assert passes; clean kernel run unaffected | 0 elaboration fatals; hello.elf PASS, Errors:0 | Trust the bench before trusting any result it reports | D-matrix (any config) | Stale/mismatched width | N/A | N/A | P0 | PASS | CLAUDE.md Gate-0 C1; commit 4c36bd82
TP-02 | Real completion trigger (C3) | Kernel completion detection | Completion must fire on real decoded EBREAK across ALL cores, not a busy-heuristic only | Run kernel_launch_test to natural completion | EBREAK decoded (0x00100073) drives completion; idle-path is warning-only fallback | hello.elf PASS, Errors:0; fallback never the primary trigger | Remove a hardcoded/binary-specific completion hack | multi-core (I1 generate loop) | Completion never fires (hang) | N/A | N/A | P0 | PASS | CLAUDE.md Gate-0 C3; commits 7764ba14, 11f71359
TP-03 | Real retirement count (C2) | Instruction count / IPC | instr_count must come from the real commit_arb_if retirement handshake, never mem_ops%3 | Tap commit_arb_if[*].valid&&ready across all lanes/cores | IPC matches a real per-lane popcount, not a fabricated ratio | vecadd: Instructions=12798, IPC=0.128 (real, non-fabricated) | A coverage/perf number must measure the real DUT, not a proxy | D-matrix | Fabricated count masking a stall | N/A | toggle: commit_arb_if.valid/ready | P0 | PASS | CLAUDE.md Gate-0 C2; commits 22115864, 11f71359
TP-04 | Honest UVM_ERROR gate (T4) | Pass/fail verdict | Gate on the true UVM_ERROR count; no '-2' subtraction hiding real errors | Run negative_result_test with +INJECT_FAULT | Injected fault is reported, not silently subtracted away | Injected corruption at 0x800075d8 detected; verdict FAIL as required | A checker never observed to fail is indistinguishable from absent | negative_dropped_store_test | Wrong-value fault injection (+INJECT_FAULT) | N/A | N/A | P0 | PASS | CLAUDE.md Gate-0 T4; commit e087a78f, validated 2026-06-29
TP-05 | Gate-0 sign-off (bidirectional SB) | End-state scoreboard | Both fault classes (wrong-value, dropped-store) must be provably catchable, standing as the permanent regression guard | +INJECT_FAULT and +DROP_STORE, re-run after every change | Both negative tests RED on injection; clean runs 0 errors | 4/4 injection guards red at defense time | No result is trustworthy until the checker is proven able to fail | every regression run | dropped store (+DROP_STORE) | N/A | N/A | P0 | PASS | CLAUDE.md Gate-0 sign-off (closed 2026-08-11); SB-DIR commit fe10b83
TP-06 | Multi-core probe generality (I1) | Probe scalability | Commit/EBREAK probes must generate over ALL clusters/sockets/cores/issue-lanes, not just core 0 | Elaborate at 2CL/2C/4W/4T and re-run C2/C3 checks | Probes scale automatically with topology, no manual re-wiring | 2CL run: probes correct with 0 code changes | A testbench that only works at one topology isn't reusable | D-matrix | N/A | N/A | N/A | P1 | PASS | CLAUDE.md Tier-1 I1; commit 11f71359
TP-07 | Topology elaboration asserts (I2) | Config integrity | UVM plusarg topology must equal the compiled RTL topology, or abort loudly at time 0 | sim-only with a deliberately mismatched CLUSTERS/CORES/WARPS/THREADS | Fatal with a named mismatch, never silent garbage | '[I2-ASSERT] NUM_CLUSTERS: plusarg=2 but RTL compiled with 1' + abort | Silent config drift is worse than a loud failure | D-matrix, all configs | stale sim-only run | N/A | N/A | P0 | PASS | CLAUDE.md Tier-1 I2; commit 37cfce55
TP-08 | SimX param-match (I3) | Golden-model config fidelity | SimX core objects must be rebuilt per-config so the golden model models the SAME topology as the DUT | Inspect simx_config.stamp after a 2CL/2C/4W/4T suite run | Stamp shows matching -D macros to the DUT build | simx_config.stamp confirmed 2CL/2C/4W/4T match, verified 2026-08-12 | A mismatched golden model makes every compare meaningless | D-matrix | N/A | N/A | N/A | P0 | PASS | CLAUDE.md Tier-1 I3
TP-09 | Passive commit probe (P1-bind) | Observability layer | bind a read-only, non-modport probe on commit_arb_if; must never act as a checker | riscv-dv stress run with the probe bound | initial assert($bits(uuid)>1) silent; 0 UVM_ERROR/FATAL | riscv-dv PASS, [P1-PROBE] assert silent | Coverage sampling must never influence pass/fail | all coverage-bearing tests | degenerate uuid width | N/A | uuid, wid, sid, tmask, PC, wb, rd, data | P1 | PASS | CLAUDE.md Tier-1 P1-bind; vx_commit_probe.sv
TP-10 | Kernel launch — native kernels | End-to-end kernel execution | Vortex kernel ELF runs to completion; DUT vs SimX end-state + lockstep compare | vecadd_lite, fibonacci, hello, tcu_mt, fpu_mt, cache_tier, lmem_stress, mshr_flood, etc. | Byte-exact end-state match, 0 lockstep mismatches | 0/0 mismatches per run; up to 32,836 words compared (wide_stress) | Prove the golden reference and the DUT agree on real workloads | riscv-dv, host_coverage_test | dropped/wrong-value fault injection | div_edge corners; text_big 232KB resident text | instr_class per unit; cache_event_cg | P0 | PASS | README Tests table; 51/51 in primary bank
TP-11 | Constrained-random base-ISA stress | riscv-dv pipeline | Google riscv-dv generates rv32im programs (M-mode CSRs stripped); run and compare vs SimX | random_instruction_stress_test, 9 profiles, 10-seed sweep | All generated programs pass; measures robustness not new coverage | 90 additional distinct programs (content-hash verified), 0 failures, +0.06% toggle only | Quantify whether more seeds buys coverage (it does not) — motivates simtgen | kernel_launch_test | single-hart race if run >1 core unmodified (OBS-027, fixed: core-gated) | arithmetic/CSR/interrupt corners | N/A | P1 | PASS | README 'measured negative result'; OBS-046
TP-12 | simtgen — divergence axis | SIMT-aware random stimulus | Original from-scratch generator produces nested-if divergence trees up to the IPDOM stack depth bound | python3 simtgen.py --axis divergence --seed N; run through kernel_launch_test | cp_split_depth reaches its max bin (d[3]), which riscv-dv/native kernels alone did not | d[3]: 0/50 seeds -> 27 hits after volatile-accumulator fix (OBS-059) | riscv-dv/Spike have no warp/mask concept; this closes that specific gap | kernel_launch_test, all configs (device-derived grid) | N/A (no self-check by design; SimX is the reference) | LLVM-folding defeat via volatile accumulator | warp_divergence_cg.cp_split_depth | P1 | PASS | docs/RTL_OBSERVATIONS.md OBS-059 + ADDENDUM; scripts/simtgen/gen_divergence.py
TP-13 | simtgen — memory axis | Bank-hostile / coalescing stimulus | Generator synthesizes coalescable / partial / scattered access patterns, plus a deliberately bank-hostile stride mode | python3 simtgen.py --axis memory --seed N | cp_bank_conflict and cp_coalesce_kind bins close, incl. the conflict bin that was previously 0 | cp_bank_conflict 0/3 -> 3/3; cp_coalesce_kind -> 3/3 (isolated merge, not yet banked) | Provoke scratchpad bank contention on purpose, not by accident | kernel_launch_test | early buggy stride caused real cross-warp address collisions (caught as 6/6 genuine MEM MISMATCH before fix) | bank-hostile idx=base+tid*nt | lmem_bank_cg.cp_bank_conflict | P1 | PASS | scripts/simtgen/gen_memory.py; docs/GENERATOR_SCOPING_DECISION.md
TP-14 | POCL / OpenCL second stimulus path | Independent compiler toolchain | Validate a second, independent code-generation path (OpenCL-C via llvm-vortex) reaches the same DUT | make all TARGET=simx; make run-simx TARGET=simx (tests/opencl/saxpy) | saxpy result verified vs expected, real perf counters reported | PASSED; instrs=41601, cycles=41711, IPC=0.997363 (independently re-run, identical) | The environment must not be provable only through one code-generation path | sim/simx baseline (vecadd_lite) | N/A | N/A | N/A | P2 | PASS | this session; runtime/simx/libvortex-simx.so built
TP-15 | AXI protocol compliance | AXI4 bus master behavior | axi_agent (active responder) checks 30 SVA assertions + 16 cover properties on all 5 AXI channels | axi_stress, axi_traffic, axi_edge kernels + throttle/flood plusargs | No protocol violation; stability assertions on aw/w/ar hold under backpressure | aw/w/ar stability 84.78->93% under +AXI_THROTTLE, byte-exact vs SimX | Prove the DUT is a well-behaved AXI master under real backpressure | cache_tier (L2/L3) | AXI error-response injection (+AXI_INJECT_ERR) | tag-buffer depth boundary | AXI cross_type_burst_size, cp_bresp | P1 | PASS | docs/RTL_OBSERVATIONS.md; VX_axi_adapter.sv
TP-16 | AXI error-injection (BUS-5/W-4) | Fault-tolerance / error handling | Inject a real AXI error response (+AXI_INJECT_ERR) and observe DUT behavior | EXTRA_PLUSARGS=+AXI_INJECT_ERR on an AXI-attached kernel | Either graceful handling or a documented, evidenced limitation | OBS-057: Vortex's AXI master hard-asserts every response must be OKAY -- NO tolerance for a real error response | Upgrade a waiver from 'declared out of scope' to 'measured and evidenced' | axi_memory_test | AXI SLVERR/DECERR response | N/A | N/A | P1 | PASS | docs/RTL_OBSERVATIONS.md OBS-057; commit 669c09b, b16e0090
TP-17 | Local-memory bank-conflict coverage (G-9) | Scratchpad bank contention | cp_bank_conflict must be reclassified so a real conflict is observable, not gated on an unreachable condition | vx_lmem_probe.sv fix (req_valid alone, not req_valid&&req_ready) + simtgen bank-hostile stimulus | conflict bin becomes non-zero under real contention | idle=70460, no_conflict=61, conflict=169 (was permanently 0) | A 0%-hit bin can be the probe's fault, not the stimulus's | simtgen memory axis | N/A | N/A | lmem_bank_cg.cp_bank_conflict | P1 | PASS | docs/RTL_OBSERVATIONS.md OBS-060 + ADDENDUM
TP-18 | riscvISACOV extension coverage | ISA functional coverage (Imperas riscvISACOV) | Generate and run the machine-readable ISA covergroups (RV32I/M/F/Zicsr/Zifencei) against the DUT via RVVI-TRACE | targeted single-kernel +ISACOV runs, gap-hunt per extension | Real (non-degenerate) coverpoints for reachable instructions | 477/481 covergroups real (99.17%, 99.57% weighted); 4 bins honestly open (2 deferred jalr imm, 2 unexplained CSR rd_sign); fence.i/nop permanently 0% by construction | Extend the standard ISA coverage model at its documented scalar boundary, don't replace it | instr_class covergroups (SIMT layer) | N/A | N/A | riscvISACOV per-extension bins | P1 | PASS | docs/RTL_OBSERVATIONS.md OBS-056, OBS-068, OBS-069; docs/riscvisacov/RISCVISACOV_INSTRUCTION_REFERENCE.md
TP-19 | Operand-sign / IEEE-754 class coverage (G-6) | ALU/LSU/FPU dispatch sign coverage | cp_imm_sign and real IEEE-754 cp_fp_class coverage across dispatch, not a placeholder covergroup | div_edge, sfu_masks, fpu_mt kernels | Sign/class combinations all sampled with real values, not a stub | G-6 fully closed 2026-09-06 | A coverage bin that always samples one constant value is not real coverage | instr_class_cg (ALU/LSU/FPU) | N/A | signed/unsigned div corners | N/A | P1 | PASS | commit 5745a70 'G-6 fully closed'
TP-20 | Div corners + commit-beat splitting (G-3/G-7) | Divider edge cases; multi-beat commit | Directed corner-case stimulus for integer division (0, -1, INT_MIN/-1) and commit-beat splitting across ISSUE_WIDTH | div_edge kernel; multi-issue commit stress | Corner values retire correctly and are distinctly covered | closed 2026-09-06, commit 7a43fce | Division-by-zero / overflow corners are exactly where hardware divider bugs hide | instr_class_cg (ALU div) | div-by-zero, INT_MIN/-1 | div corner values | N/A | P1 | PASS | commit 1fa71a2a6, 7a43fce
TP-21 | Register-hazard coverage, WAR unreachable (G-4) | RAW/WAW/WAR hazard classification | VX_scoreboard hazard detector can only ever produce RAW/WAW by construction; WAR is structurally unreachable, not a stimulus gap | directed hazard-stress kernels | RAW/WAW sampled with real values; WAR correctly waived, not silently ignored | closed 2026-09-04; OBS-055 documents why WAR is structurally unreachable | Distinguish 'unreachable by design' from 'untested' before waiving anything | instr_class_cg | N/A | N/A | hazard_cg RAW/WAW | P1 | PASS | commit 6faa6e2; OBS-055
TP-22 | Config matrix run (D-matrix) | Cross-topology regression | Run the full suite across 1C/1W, 1C/4W, 2C/4W, 2CL/2C/4W and bank each before the next config overwrites cov/merged.ucdb | bash scripts/run_suite.sh at each topology; copy bank before next run | Per-config bank verified by re-reading the copy; never blend UCDBs across configs | 1CL banked clean 51/51 = 94.72% (2026-08-18/20); 2CL 50/50 = 94.55%; 2CL+L2+L3 51/51 = 93.18% | A cross-config UCDB merge is invalid (per-instance width/count changes) | SIGN (aggregates all banks) | N/A | N/A | N/A | P0 | WIP | CLAUDE.md Tier-3 D-matrix -- PARTIAL: simtgen-closed bins not yet folded into these banks (isolated merge only)
TP-23 | Merged sign-off report (SIGN) | Final regression closure | One report: seeded regression pass rate, merged functional+code coverage vs goal, matrix status | aggregate all banked configs + findings register | Single, defensible closing statement of verified scope and open items | not yet produced | Closes last, and only once every upstream box is genuinely closed | D-matrix | N/A | N/A | N/A | P0 | BLOCK | Blocked on: D-matrix full closure + a full-suite re-run folding simtgen's 3 closed bins into the banked totals
TP-24 | Exception/interrupt stimulus (T-exc) | Trap/exception coverage | Directed ebreak / misaligned / illegal-instruction stimulus to drive exception_cg -- note: Vortex terminates via tmc x0 -> busy deassertion, NOT ebreak (OBS-024) | not yet built | stimulus reaches DUT; exception bins populate | not yet started | Vortex has no trap architecture in the conventional sense -- two riscv-dv profiles are unimplementable for this reason | kernel_launch_test | misaligned access (OBS-013, sim-only assertion is the only guard today) | misaligned addr corner | exception_cg | P2 | WIP | CLAUDE.md Tier-2 T-exc; must be designed around OBS-024, not the old ebreak assumption
TP-25 | Cache coherence directed test (T-cache) | Multi-core/multi-access cache behavior | Directed multi-core cache access + eviction scenarios, end-state compare vs SimX, feeds cache coverage | not yet built | passes bidirectional vs SimX | not yet started | Weakly-coherent (flush-only) memory model -- a fenceless cross-core kernel has no architecturally-defined result and must not be mistaken for a bug | cache_tier, L2/L3 sweep | fenceless cross-cluster race (OBS-009, expected/not-a-bug) | N/A | cache_event_cg per instance | P2 | WIP | CLAUDE.md Tier-2 T-cache

## Traceability Matrix
Traceability Matrix — Spec ↔ Requirements ↔ Test Cases
Requirement Coverage Closure: Verified = COUNTIF(L5:L50,"PASS") / Total Reqs
Req ID | Spec Section & Reference | Requirement Description | Feature | Mapped Test Cases | Verification Method | Coverage Type | Pass Criteria | Priority | Verified By | Status | Closure Notes
R-001 | CLAUDE.md Gate-0 C1 | UVM tag/ID width must equal the elaborated RTL VX_MEM_TAG_WIDTH | AXI/mem tag width | TP-01 | Simulation + elaboration assert | Directed | 0 fatals; correct width reported | P0 | Samuel Moussa | PASS | commit 4c36bd82
R-002 | CLAUDE.md Gate-0 C3 | Completion trigger must be the real decoded EBREAK across all cores | Kernel completion | TP-02 | Simulation | Directed | EBREAK-driven completion, fallback is warning-only | P0 | Samuel Moussa | PASS | commits 7764ba14, 11f71359
R-003 | CLAUDE.md Gate-0 C2 | Instruction count/IPC must derive from the real commit_arb_if handshake | Instr count / IPC | TP-03 | Simulation | Directed | non-fabricated IPC value | P0 | Samuel Moussa | PASS | commits 22115864, 11f71359
R-004 | CLAUDE.md Gate-0 T4 | Verdict gate must use the true UVM_ERROR count, no subtraction | Pass/fail verdict | TP-04 | Simulation, fault injection | Negative | injected fault reported as FAIL | P0 | Samuel Moussa | PASS | commit e087a78f
R-005 | CLAUDE.md Gate-0 sign-off | Both wrong-value and dropped-store fault classes must be provably catchable (bidirectional scoreboard) | End-state scoreboard | TP-05 | Simulation, fault injection | Negative | 4/4 injection guards red | P0 | Samuel Moussa | PASS | SB-DIR fe10b83; closed 2026-08-11
R-006 | CLAUDE.md Tier-1 I1/I2/I3/I5/P1-bind | Probes/asserts/golden model must generalize over the full config space, not one topology | Configurability | TP-06,TP-07,TP-08,TP-09 | Simulation, elaboration | Directed | topology mismatch aborts loudly; correct at every tested config | P1 | Samuel Moussa | PASS | commits 11f71359, 37cfce55; simx_config.stamp verified 2026-08-12
R-007 | CLAUDE.md Tier-3 D-matrix | Full config matrix (1C/1W .. 2CL/2C/4W) must be run and banked, never blended | Cross-topology regression | TP-22 | Simulation, regression | Functional+code | per-config bank re-read and verified | P0 | Samuel Moussa | WIP | 1CL/2CL/2CL+L2L3 banked; simtgen-closed bins not yet folded in
R-008 | CLAUDE.md Tier-3 SIGN | One merged sign-off report over all banks + findings | Final closure | TP-23 | Review | N/A | single defensible closing statement | P0 | Samuel Moussa | BLOCK | blocked on R-007 + a full-suite re-run
R-009 | VERIFICATION_PLAN_v2 G-9 / OBS-060 | cp_bank_conflict must be classified on a reachable RTL condition (req_valid), not req_valid&&req_ready | Scratchpad bank contention | TP-17 | Simulation | Functional | conflict bin non-zero under contention | P1 | Samuel Moussa | PASS | idle=70460,no_conflict=61,conflict=169; commit ccbdc7e06
R-010 | VERIFICATION_PLAN_v2 G-6 | Real IEEE-754 class + operand-sign coverage across ALU/LSU/FPU dispatch | ALU/LSU/FPU sign/class coverage | TP-19 | Simulation | Functional | non-degenerate sign/class bins | P1 | Samuel Moussa | PASS | commit 5745a70
R-011 | VERIFICATION_PLAN_v2 G-3/G-7 | Division corner values + multi-beat commit splitting covered | Divider corners; commit beats | TP-20 | Simulation | Functional | corner values retire and are distinctly covered | P1 | Samuel Moussa | PASS | commit 1fa71a2a6, 7a43fce
R-012 | VERIFICATION_PLAN_v2 G-4 / OBS-055 | RAW/WAW hazard coverage real; WAR correctly waived as structurally unreachable | Register hazard classification | TP-21 | Simulation + RTL analysis | Functional | WAR waiver evidence-based, not silent | P1 | Samuel Moussa | PASS | commit 6faa6e2
R-013 | VERIFICATION_PLAN_v2 BUS-5/W-4 / OBS-057 | AXI error-response handling must be measured, not assumed out of scope | AXI fault tolerance | TP-16 | Simulation, fault injection | Negative | evidenced disposition (finding, not silent waiver) | P1 | Samuel Moussa | PASS | commit 669c09b, b16e0090
R-014 | docs/RTL_OBSERVATIONS.md OBS-056, OBS-068, OBS-069 | riscv-isacov-style ISA covergroups (RV32I/M/F/Zicsr/Zifencei) must run against the DUT via RVVI-TRACE | ISA functional coverage | TP-18 | Simulation | Functional (ISA) | non-degenerate coverpoints for reachable instrs | P1 | Samuel Moussa | PASS | 477/481 = 99.17% real (up from 83.14% at 2026-09-06 freeze, 3 gap-hunt rounds 2026-09-20); 2 permanently structurally dead (fence.i, nop); 4 bins honestly open (see RISCVISACOV_STATUS.md, RISCVISACOV_INSTRUCTION_REFERENCE.md)
R-015 | docs/GENERATOR_SCOPING_DECISION.md | A SIMT-aware random generator must exist; reuse only if genuinely separable from its checking stack | SIMT stimulus diversity | TP-12,TP-13 | Design review + simulation | N/A | documented feasibility decision + working generator | P1 | Samuel Moussa | PASS | FuzzGPU generator ruled out (inseparable); simtgen built original
R-016 | docs/RTL_OBSERVATIONS.md OBS-059 | Divergence-axis stimulus must reach the IPDOM stack's max depth bin (d[3]) | Divergence-depth coverage | TP-12 | Simulation | Functional | cp_split_depth 4/4 | P1 | Samuel Moussa | PASS | 0/50 seeds -> 27 hits after volatile-accumulator fix
R-017 | this session, POCL validation | A second, independent compiler toolchain (OpenCL-C) must reach the same DUT | Toolchain diversity | TP-14 | Simulation | N/A | real workload PASSED with real perf counters | P2 | Samuel Moussa | PASS | saxpy PASSED, instrs=41601,cycles=41711,IPC=0.997
R-018 | docs/RTL_OBSERVATIONS.md OBS-061 | Primary RV32IMF config's actual elaborated FLEN/MISA-D state must be confirmed dynamically, not assumed | Configuration fidelity | none yet -- new finding | Isolated elaboration probe | N/A | dynamic proof, not just static grep | P1 | Samuel Moussa | BLOCK | OPEN: FLEN=64/MISA D=1 confirmed; 4 scoping follow-ups unresolved
R-019 | docs/RTL_OBSERVATIONS.md R10 / OBS-045 | Reset relay must not leave reset_o at X for one cycle | Reset integrity | kernel_launch_test regression | Simulation, restored assertion | Directed | 0 X-window; branch coverage re-measured honestly after fix | P0 | Samuel Moussa | PASS | fixed here; still present upstream; coverage correctly DROPPED 95.1%->94.5%
R-020 | docs/RTL_OBSERVATIONS.md R1 / OBS-012, OBS-058 | JALR LSB-clear deviation from RISC-V spec must be logged with disposition | ISA-compliance defect | riscv-dv, simtgen divergence kernels | Simulation + external cross-reference | Directed | logged, disposition stated, independently corroborated | P1 | Samuel Moussa | PASS (logged) | present upstream at HEAD; independently found by FuzzGPU (USENIX Sec'26)

## Feature Coverage
Feature & Negative Scenario Coverage
A — Feature Coverage & Cascaded (Mix & Match) Scenarios
Feature ID | Feature Name | Primary Test Cases | Cascaded Feature | Cascaded Test Case | Mix & Match Intent | Coverage %
FC-01 | instr_class_cg (ALU/LSU/SFU) | riscv-dv, div_edge, sfu_masks | Warp-mask cross | <uniform/partial,op> | op x active-thread-mask cross, per execution unit | 100% (op-decoded)
FC-02 | instr_class_cg (FPU) | fpu_test, fpu_mt, diverge_fpu | Partial-mask cross | <partial[2..3],fpu_op> | FP ops under peeled thread masks | 100% (fcvt/fnmadd fix)
FC-03 | instr_class_cg (TCU) | tcu_test, tcu_mt | Warp-collective cross | <uniform,wmma> | multi-warp WMMA collective op | 100% (multi-warp fix)
FC-04 | warp_divergence_cg.cp_split_depth | simtgen (divergence axis) | IPDOM stack depth 0..3 | d[0..3] x nested-if | reconvergence-stack depth fully sampled | 4/4 = 100% (was 3/4)
FC-05 | lmem_bank_cg.cp_bank_conflict | simtgen (memory axis, bank-hostile stride) | LMEM bank x conflict state | idle/no_conflict/conflict | scratchpad bank contention observed for real | 3/3 = 100% (was 0/3)
FC-06 | coalesce_cg.cp_coalesce_kind | simtgen (memory axis, 3 patterns) | access-pattern x warp size | coalescable/partial/scattered | memory-coalescing classification | 3/3 = 100%
FC-07 | cache_event_cg (L1 I$/D$) | cache_stress, cache_tier, mem_zero | hit/miss x cache instance | icache write-port waiver (WRITE_ENABLE=0) | structural waivers evidence-cited per instance | 398/403 = 98.75%
FC-08 | cache_event_cg (L2/L3, shared) | cache_tier @2CL+L2+L3 | hit/miss x 4 shared instances | first exercise of shared tiers (was PASSTHRU) | 196,868-word byte-exact compare | hit+miss on all 4 instances, 13k-15k hits ea.
FC-09 | dcr_cg (DCR RAL read-back) | host_coverage_test | per-core RAL x write value | DCR write-during-busy race (OBS-025), disposition OPEN | peek-only bind probe, never a write-back path | 15/15 checked, 0 failed
FC-10 | riscvISACOV (RV32I/M/F/Zicsr/Zifencei) | targeted single-kernel +ISACOV gap-hunt (isacov_fill, 3 rounds) | instruction x operand, machine-readable ISA-derived | extends the standard model at its scalar boundary, does not replace it | extends the standard model at its scalar boundary, does not replace it; per-instruction detail in riscvisacov/RISCVISACOV_INSTRUCTION_REFERENCE.md | 477/481 = 99.17% (99.57% weighted), up from 83.14% at the 2026-09-06 freeze
B — Negative Scenarios
Neg ID | Negative Scenario | Feature | Expected DUT Behavior | Error Type | Linked TC | Priority
NEG-01 | Wrong-value fault injection (+INJECT_FAULT) | End-state scoreboard | checker reports FAIL at the exact injected address | data corruption | TP-04, TP-05 | P0
NEG-02 | Dropped-store fault injection (+DROP_STORE) | End-state scoreboard (reverse pass) | checker reports FAIL -- a word SimX wrote that the DUT never did | silent store loss | TP-05 | P0
NEG-03 | AXI error-response injection (+AXI_INJECT_ERR) | AXI master error path | measured DUT behavior on a real SLVERR/DECERR | bus protocol error | TP-16 | P1
NEG-04 | riscv-dv on >1 core, unmodified (OBS-027) | Multi-core store ordering | architecturally undefined without core-gating -- correctly excluded, not a false pass | single-hart-in-multihart race | TP-11 | P1
NEG-05 | Fenceless cross-cluster kernel (OBS-009) | Weak-coherency memory model | DUT/SimX divergence is EXPECTED, not a bug -- must not be misclassified as a failure | undefined cross-core ordering | TP-25 (T-cache) | P2
NEG-06 | Misaligned data access, no trap (OBS-013) | Exception/trap architecture | silently retargeted/torn access; sim-only RUNTIME_ASSERT is the only guard | misaligned load/store | TP-24 (T-exc) | P2
NEG-07 | Buggy generator stride -> real cross-warp collision | simtgen memory-axis dev iteration | caught as 6/6 genuine scoreboard MEM MISMATCH before the fix landed | stimulus-bug false failure, correctly diagnosed not silenced | TP-13 | P1

## Corner Cases
Corner Cases, Toggle Coverage & Data Scenarios
A — Data Corner Cases
CC ID | Signal / Parameter | Corner Case Value | Rationale | Expected Behavior | Linked TC | Priority
CC-01 | Integer divider operands | 0, -1, INT_MIN / -1 | classic division-by-zero / overflow corners hide hardware divider bugs | architecturally-defined result per RISC-V spec, no trap | TP-20 | P1
CC-02 | IEEE-754 FP class | NaN, +/-Inf, subnormal, signed zero | exercise cp_fp_class with real, non-degenerate values | real class value, not a constant stub | TP-19 | P1
CC-03 | fsqrt.s result | values probing the 1-ULP boundary | OBS-014: hardware fsqrt.s deviates 1 ULP from IEEE-correct | known, disclosed 1-ULP deviation (accuracy limitation, logged as a finding) | fpu_test | P2
CC-04 | Misaligned load/store address | addr not aligned to access width | no trap in this DUT; silently retargeted/torn (OBS-013) | sim-only RUNTIME_ASSERT is the only guard -- must not silently pass | TP-24 (T-exc) | P1
CC-05 | IPDOM divergence-stack depth | d = 0,1,2,3 (NUM_THREADS-1 bound) | the RTL-derived reconvergence-stack bound (VX_gpu_pkg.sv:53) | cp_split_depth samples every depth, incl. d[3] | TP-12 (simtgen) | P1
CC-06 | Scratchpad bank index collision | idx = base + tid*nt (deliberately bank-hostile) | provoke real contention rather than hope for it by chance | conflict bin non-zero, no false address collision | TP-13, TP-17 | P1
CC-07 | JALR target LSB | odd computed target address | OBS-012/R1: JALR does not clear the LSB, an ISA-spec deviation | logged disposition; odd PC propagates via AUIPC -- not silently ignored | TP-20, riscv-dv | P1
CC-08 | AXI burst size / response | native DATA_SIZE-derived awsize; injected SLVERR/DECERR | structural reachability boundary + real fault tolerance measurement | cp_size 100% (native only, evidence-cited); AXI error path measured (OBS-057) | TP-15, TP-16 | P1
CC-09 | Reset relay timing window | 1 cycle immediately after RESET_RELAY deassertion | OBS-045/R10: reset_o was X for one cycle, nothing resets the relay flop | 0 X-window after fix; branch coverage honestly re-measured (95.1%->94.5%) | kernel_launch_test regression | P0
CC-10 | Primary config FLEN / MISA-D bit | RV32IMF config as elaborated (not as named) | OBS-061: dynamically confirmed FLEN=64, MISA D-bit=1 -- contradicts the 'RV32IMF, no D' assumption | OPEN -- reachability/soundness/coverage-dilution scoping not yet complete | none yet -- new finding | P1
B — Toggle Coverage Plan
TGL ID | Signal Name | Toggle Type | Condition to Trigger | Test Cases | Target % | Measured %
TGL-01 | icache write-data path (512b) | 0->1->0 on write-data bus | icache elaborated with WRITE_ENABLE=0 (read-only) | cache_stress, cache_tier | 0% (structural) | 0% -- structurally undrivable, evidence-cited waiver (OBS-033)
TGL-02 | icache response-data path | 0->1->0 on read-response bus | positive control proving the read direction IS alive | cache_stress, cache_tier | 100% | toggles on all 512 bits -- confirms only the WRITE direction is dead
TGL-03 | dcache write-through data path | 0->1->0 on cache write-data | write-through (no write-back) cache; still the dominant reachable subtree | wide_stress, mem_stress, mshr_flood | target: max reachable | 89% measured
TGL-04 | 44-bit UUID counter bits [18:31] | full toggle across the retire-tag counter width | OBS-034: bits no simulation can ever toggle at current run lengths -- infeasible, NOT waived | every retiring instruction | not targeted for 100% -- deliberately left honest | OPEN, not waived (infeasible != structurally dead)
TGL-05 | AXI b_valid_stable | stability of BVALID across a full write-response window | adapter hardwires m_axi_bready=1'b1 (write-through, fire-and-forget) | axi_stress, axi_traffic | 0% (structural) | excluded -- structurally unreachable, evidence-cited (VX_axi_adapter.sv:313)
TGL-06 | AXI r_valid / r_data_stable | stability of RVALID/RDATA under slave backpressure | reachable in principle, but the DUT's read buffer never forces rready to drop under +AXI_FLOOD | axi_edge (+AXI_FLOOD) | target: reachable | left honestly uncovered -- reachable but not hit, NOT waived
TGL-07 | commit_arb_if.valid / ready (all lanes) | toggling across all ISSUE_WIDTH lanes, all cores | feeds the real (non-fabricated) instruction-count/IPC measurement | every kernel_launch_test run | 100% intended | verified via C2 fix, commits 22115864/11f71359

## Test Environment
Test Environment & Methodology
Verification Methodology
Methodology | Simulation -- directed native kernels + constrained-random (Google riscv-dv via core-v-verif) + an original SIMT-aware random generator (simtgen) + a second compiler path (POCL/OpenCL-C). No formal/emulation/FPGA in this project's scope.
Simulator / Tool | Siemens QuestaSim 2021.2_1
Formal Tool | N/A -- no formal property verification in scope (see README Scope and limits)
Coverage Closure Goal | Total (banked): 94.72% / 94.55% / 93.18% across 3 configs, never blended. Covergroup bins 370/377=98.1% (primary). Line/stmt 98.1%, branch 94.5%, assertions 96.9%, SVA directives 100%.
Regression Framework | Custom Makefile (run.sh -> prepare.sh -> compile.sh -> simulate.sh) + run_suite.sh regression driver + UVM 1.2 test library
DUT Configuration
DUT Name / Version | Vortex GPGPU, RTL pinned at upstream 7a52ee5 + this project's local RTL/TB fixes (git submodule, branch fft-poc)
RTL Top Module | Vortex.sv (native cache-line bus) / Vortex_axi.sv = Vortex.sv + VX_axi_adapter (AXI4, primary)
Clock Frequency | N/A -- functional RTL simulation only, no target implementation frequency
Reset Polarity | Active-High, Asynchronous assert / synchronous-to-clk deassert (always @(posedge clk or posedge reset); see OBS-045 for the VX_reset_relay one-cycle X-window finding and its fix)
Technology Node | N/A -- front-end functional verification only; no synthesis/technology mapping in scope
Synthesis Constraints | N/A -- not applicable at this verification stage
Testbench Architecture
TB Top | vortex_tb_top.sv
Interface / VIF | vortex_axi_if (AXI4, primary) / vortex_mem_if (native) / vortex_dcr_if / vortex_status_if / vortex_if (misc SVA)
Scoreboard | Present -- two independent scoreboards: bidirectional end-state (vortex_scoreboard.svh) + per-instruction lockstep (lockstep_scoreboard.svh)
Functional Coverage | Present -- 19-20 original SIMT covergroups (divergence, coalescing, bank-conflict, cache events, DCR, AXI crosses, instr-class per execution unit) + extended riscvISACOV RV32I/M/F/Zicsr/Zifencei coverage
Assertions (SVA) | Present -- 30 AXI SVA assertions + 16 AXI cover properties, plus per-interface SVA on mem/dcr/status/misc interfaces
Reference Model | Present -- SimX (primary, DPI-C, cycle-approximate, recompiled per config) + Spike (secondary, independent, base-ISA/warp0/lane0 cross-check only)
Pass / Fail Infrastructure
Mismatch Detection | Bidirectional scoreboard comparison: DUT memory/console vs SimX end-state (every DUT-written word AND every SimX-written word the DUT never wrote), plus per-lane per-instruction lockstep (PC/rd/value) vs SimX, cross-checked offline vs Spike on the base-ISA subset
X / Z Propagation | Not available -- QuestaSim 2021.2_1 has no -xprop flag on this toolchain (confirmed); X-propagation analysis is an explicit non-goal, stated in README Scope and limits
Timeout Watchdog | Per-test TIMEOUT plusarg, measured per program (e.g. text_big needs 490,468 cycles; riscv-dv default 205,982); RTL-side STALL_TIMEOUT watchdog (OBS-011 fixed: was 1**N=1, never scaled)
Log / Report Format | results/<date>/run_<time>_<test>/ -- full transcript + pass/fail SUMMARY.txt + per-run coverage.ucdb; merged via vcover into per-config banks under cov/bank_<CFG>/

## Sign-off & Review
Sign-off & Review
A — Approval Signatures
Role | Name | Department | Date | Signature / Sign-off
Test Plan Author | Samuel Moussa | Digital Verification (solo) | 2026-09-07
Design Lead | N/A -- solo project, no separate design-lead role | -
Verification Lead | Samuel Moussa | Digital Verification (solo) | 2026-09-07
Project Manager | N/A -- academic graduation project, no PM role
Quality Assurance | Dr. Hassan Aboushady / Dr. Alhassan Sayed (academic review) -- Assoc. Prof. Dr. Alhassan Sayed, Supervisor; mentored by Dr. Hossam Hassan
B — Review Comments
# | Reviewer | Section | Comment | Resolution / Action
1 | Claude (Opus/Sonnet review pass) | D-matrix / SIGN | D-matrix is PARTIAL: 1CL/2CL/2CL+L2L3 banked clean, but 2CL was blocked historically on FW-1b duplicate-test + budget fixes | Both since resolved in-tree per run_suite.sh; re-verify before SIGN is closed
2 | Claude (Opus/Sonnet review pass) | OBS-061 / RV32D | Primary config elaborates FLEN=64/MISA D=1, contradicting the assumed 'RV32IMF, no D' scope | Confirmed dynamically via isolated elaboration probe; 4 scoping follow-ups (reachability, bank dilution, SimX F-only soundness, intent) remain OPEN
3 | Claude (Opus/Sonnet review pass) | simtgen coverage closures | 3 bins closed (cp_split_depth, cp_bank_conflict, cp_coalesce_kind) are in ISOLATED merges, not the frozen banked totals | Do not quote as part of 94.72/94.55/93.18% until a full-suite re-run folds them in -- tracked, not silently assumed
4 | Claude (Opus/Sonnet review pass) | Generator scope | FuzzGPU's generator was evaluated for reuse and found inseparable from its checking stack | Documented as a negative result in docs/GENERATOR_SCOPING_DECISION.md; simtgen built original instead, axis taxonomy only reused as a label
5
6
7
8
C — Overall Plan Verdict
Verdict: |  |  | APPROVED WITH COMMENTS -- Gate-0 and Tier-1 fully closed and evidenced; Tier-2 (T-cache, T-exc) and Tier-3 (D-matrix full closure, SIGN) remain open per the Test Plan sheet; OBS-061 is an open scoping item to resolve before final sign-off.

## Revision History
Revision History
Rev | Date | Author | Approved By | Description of Changes
v0.1 | 2025-10-23 | Samuel Moussa (+ initial team) | - | Initial commit -- Vortex GPGPU UVM GP project scaffolded, README + verification plan draft
v0.2 | 2026-03-19 .. 2026-04-10 | Samuel Moussa | - | UVM environment bring-up: env pkg refactor, DPI-C/analysis imports, mem_agent + AXI/functional-memory virtual sequences, SimX DPI integration stabilized
v0.3 | 2026-05-05 .. 2026-06-24 | Samuel Moussa | - | Major architectural restructure: sim-flow fixes, execution tracking, AXI protocol verification, scoreboard delegated to DUT memory responses; real SimX-based scoreboard overhaul; first negative fault-injection test added
v0.4 | 2026-06-26 .. 2026-06-29 | Samuel Moussa | - | Gate-0 closed: C1 (tag width), C3 (real EBREAK completion), C2 (real retirement count), T4 (honest error gate); INV-1 solved (printf-light kernels); negative_result_test proven non-vacuous
v0.5 | 2026-07-08 .. 2026-07-10 | Samuel Moussa | - | Coverage pushed 79.2%->91.0% (1CL); 2CL riscv-dv divergence root-caused (weak-coherency, not a DUT bug); config-aware coverage exclusions introduced
v0.6 | 2026-08-06 .. 2026-08-12 | Samuel Moussa | - | A3 (golden-halt discipline), A6 (Spike independence audit), B1 (DCR RAL), B2 (single-source scoreboard), SB-DIR (bidirectional/dropped-store) all closed; Gate-0 formally signed off; 1CL banked clean 45/45=91.08%
v0.7 | 2026-08-15 .. 2026-08-20 | Samuel Moussa | - | Coverage maximized to 94.72%/94.55%; icache toggle root-caused (WRITE_ENABLE=0); R10 reset-relay X-window found+fixed; UVM testbench repackaged into Vortex/sim/uvmsim as a real git submodule
v0.8 | 2026-09-03 .. 2026-09-04 | Samuel Moussa | - | riscvISACOV gap-hunt (OBS-056, 78/80 real); G-4/register-hazard + OBS-054/055 closed; PPT/diagram handoff report for review
v0.9 | 2026-09-05 .. 2026-09-06 | Samuel Moussa | - | G-3/G-6/G-7 closed; G-9 partial (lmem bank-conflict probe); BUS-5/W-4 upgraded via OBS-057 AXI error injection; whole-project PPT handover drafted
v1.0 | 2026-09-07 | Samuel Moussa | pending formal review | G-9 fully closed (OBS-060 probe fix); simtgen (original SIMT-aware random generator, divergence+memory axes) built and coverage-verified; POCL/OpenCL toolchain validated end-to-end; OBS-061 (FLEN=64) found and logged as open; README rewritten as a standard, reusable, fully-configurable UVM framework; this test-plan workbook filled from project history
v1.1 | 2026-09-20 | Samuel Moussa | - | riscvISACOV L1 gap-hunt re-opened and taken from 83.14% (2026-09-06 freeze) to 99.17% (477/481 bins, 99.57% weighted) over 3 stimulus rounds, each re-verified byte-exact under LOCKSTEP before banking; new per-instruction reference doc (RISCVISACOV_INSTRUCTION_REFERENCE.md, all 80 covergroups); OBS-068 (branch/jal disassembly parsing bug) and OBS-069 (open lhu sign anomaly) found and disclosed; Coverage_Model_Reference.md stale-figure reconciled